## Sheet1
Part Number | Description | Criticality | Samples qty | Status | Picture | Remarks
S1A28862 | Terminal plug-in low rating | MAJOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
S1A28863 | Terminal plug-in high rating | MAJOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
GHJ16013AA | Spreader1 4P | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
GHJ16016AA | Spreader4 4P | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
GHJ16014AA | Spreader2 4P | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
GHJ16015AA | Spreader3 4P | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187114AA | PLATE, SLIDE | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Finished Trial and Sample Submission
48187099AA | PLATE, CAM | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187081AA | CLAMP, SHAFT | CRITICAL | 30 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187077AA | LEVER, DOOR LOCK | CRITICAL | 30 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187083AA | STRIKER-PLATE | MINOR | 10 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187082AA | LOCK, SHAFT | CRITICAL | 30 | Sent to JR-TH ,3-Sep-2026 |  | Samples received
48187087AA | LEVER, SHAFT RELEASE | CRITICAL | 30 | Sent to JR-TH ,3-Sep-2026 |  | Finished Trial and Sample Submission
Samples in pipeline:
Part Number | Description | Criticality | Samples Required | Status | Picture | Remarks
48187076AA | LATCH, UVR | CRITICAL | 30 | Samples Preparation in progress |  | Finished Trial and Sample Submission
S1B22575 | TERMINAL Connection(ithSILVER TIP) | MAJOR | 10 | Samples Preparation in progress |  | Samples not yet Received
S1B22372 | TERMINAL Connection(/O SILVER TIP) | MAJOR | 10 | Samples Preparation in progress |  | Samples not yet Received
S1A23987 | ARC STACK LOW | CRITICAL | 30 | Samples Preparation in progress |  | Samples not yet Received
48187145AA | STAPLE | CRITICAL | 30 | Samples Preparation in progress |  | Samples not yet Received